## Bug Log
Bug Metrics Formula: |  | 1 x num (low) + 5 x num (high) + 10 x num (critical)
*First line of the table is illustrated as an example.
Bug Metrics
S/N | Iteration | Function | Description | Severity (Low/High / Criticial) | Points | Total score | Status (Pending/Solved) | Date Discovered | Date Resolved | Debug Pair Name | Action Plan
e.g. 1 | 2 | Login | <description of the problem> | <see above table> | <see above table> |  | <solved / pending >
1 | 2 | Login | Enter admin into username input field and password input field. Click Submit. Unable to redirect to adminHomepage | High | 5 | 16 | solved | 21/09/16 | 21/09/16 | Ming Kwang Eugene | Resolved in planned debugging time in the iteration
2 |  | View All Courses | Check that all the courses displayed are sorted by courseCode and courseCode in ascending order | Low | 1 |  | solved | 2016-09-24 | 2016-09-24 | Cristabel Yew Kit | Resolved in planned debugging time in the iteration
3 |  | Search | Display no search results when Student entered an invalid course code | High | 5 |  | solved | 2016-09-24 | 2016-09-24 | Cristabel Yew Kit | Resolved in planned debugging time in the iteration
4 |  | Search | Display no search results when Student search with course name | High | 5 |  | solved | 2016-09-24 | 2016-09-24 | Cristabel Yew Kit | Resolved in planned debugging time in the iteration
5 | 3 | Unzip & Extract Function | Upload .zip files and the csv files are extracted successfully with errors (No folder contained in the zip file) | High | 5 | 28 | solved | 2016-09-27 | 2016-09-27 | Cristabel Wilson He | Resolved in planned debugging time in the iteration
6 | 3 | Unzip & Extract Function | System did not delete the .zip file (with no folder) in the uploads folder | Low | 1 |  | solved | 2016-09-27 | 2016-09-27 | Cristabel Wilson He | Resolved in planned debugging time in the iteration
7 | 3 | Unzip & Extract Function | Failed to display error message when user uploaded files which does not end with .zip | Low | 1 |  | solved | 2016-09-27 | 2016-09-27 | Cristabel Wilson He | Resolved in planned debugging time in the iteration
8 | 3 | Bidding Cart Function | Student allowed to checkout cart when exam timetable clashes with cart/bid items | High | 5 |  | solved | 2016-02-10 | 2016-03-10 | Eugene, Wilson He | Resolved in planned debugging time in the iteration
|  |  | Student allowed to checkout cart when timeslot clashes with cart/bid items | High | 5
|  |  | No error displayed when blank input is added to bidAmount and checkout is refused | Low | 1
9 | 3 | Bootstrap Function | Unable to upload zip files to Amazon AWS | High | 5 |  | solved | 2016-09-27 | 2016-09-27 | Cristabel Wilson He | Resolved in planned debugging time in the iteration
10 | 3 | Start/End Generate Bids Function | Logic to generate successful bids for round 1 did not adhere to the requirements. It allowed multiple bids at the clearing price to be accepted. | High | 5 |  | solved | 2016-10-05 | 2016-10-05 | Cristabel Wilson He | Resolved in planned debugging time in the iteration
11 | 4 | Bootstrap Function | Unable to read all the csv files after unzipping the zip file at Amazon AWS (OS dependencies, Linux) | High | 5 | 33 | solved | 2016-10-10 | 2016-10-10 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
12 | 4 | Student Timetable Function | Unable to read timetable JSON file on Amazon AWS | High | 5 |  | solved | 2016-10-10 | 2016-10-10 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
13 | 4 | Json Delete Bid Function | Unable to drop student bid | High | 5 |  | solved | 14/10/2016 | 14/10/2016 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
| 4 | Json Delete Bid Function | Incorrect error message for invalid token | High | 1 |  | solved | 14/10/2016 | 14/10/2016 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
14 | 4 | Json Drop Section Function | Incorrect error message for invalid token | Low | 1 |  | solved | 2016-10-16 | 2016-10-16 | Cristabel, Ming Kwang | Resolved in planned debugging time in the iteration
15 | 4 | Json Drop Section Function | Incorrect order of error messages | Low | 1 |  | solved | 2016-10-16 | 2016-10-16 | Cristabel, Ming Kwang | Resolved in planned debugging time in the iteration
16 | 4 | Json Dump User Function | Incorrect error message for blank r and missing token | Low | 1 |  | solved | 2016-10-16 | 2016-10-16 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
17 | 4 | Json Dump User Function | Incorrect error message for missing r and missing token | Low | 1 |  | solved | 2016-10-16 | 2016-10-16 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
18 | 4 | Json Dump bid Function | Incorrect error message for Invalid course | Low | 1 |  | solved | 2016-10-16 | 2016-10-16 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
19 | 4 | Json Dump bid Function | Declare both arraylist successfulBids and unsuccessful in the wrong method in BidDAO | High | 5 |  | solved | 2016-10-16 | 2016-10-16 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
20 | 4 | Json Dump Table Function | Exception is not displayed when caught | Low | 1 |  | solved | 18/16/2016 | 18/16/2016 | Eugene, Ming Kwang | Resolved in planned debugging time in the iteration
21 | 4 | Json Dump Section Function | Incorrect error message for invalid section | Low | 1 |  | solved | 2016-10-19 | 2016-10-19 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
22 | 4 | Json Dump Section Function | Incorrect error message valid section | Low | 1 |  | solved | 2016-10-19 | 2016-10-19 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
23 | 4 | Json Dump Section Function | Incorrect error message for Invalid course | Low | 1 |  | solved | 2016-10-19 | 2016-10-19 | Quek Yew Kit Wilson He | Resolved in planned debugging time in the iteration
27 | 4 | Json update bid Function | Incorrect error message forAdmin tries bidding with amt lesser than minimum bid in round 2 | Low | 1 |  | solved | 2016-10-22 | 2016-10-25 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration 5
28 | 4 | Json update bid Function | Incorrect error message for Admin tries bidding when exam timetable timeslot for the section clashes with that of a previously bidded section for the student | Low | 1 |  | solved | 2016-10-22 | 2016-10-25 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration 5
29 | 4 | Json update bid Function | Incorrect error message for Admin tries updating a bid when student has 5 sections bidded | Low | 1 |  | solved | 2016-10-22 | 2016-10-25 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration 5
30 | 5 | Json update bid Function | Incorrect error message shown when user is eligible to bid for the course in round 2 but it shows bid too low | High | 5 | 56 | solved | 2016-10-25 | 2016-10-25 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration
31 | 5 | Json delete bid Function | Incorrect error message shown when user did not place any bids | High | 1 |  | solved | 2016-10-28 | 2016-10-28 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration
32 | 5 | Json drop section Function | Incorrect error message displayed incorrectly when user enter the correct course id and section id. [Converted the string in Bids to upperCase) | High | 1 |  | solved | 2016-10-28 | 2016-10-28 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration
33 | 5 | Login Function | Unable to locate the servlet because of duplicate names for JSON Login and Login Function | High | 5 |  | solved | 2016-10-28 | 2016-10-28 | Ming Kwang Wilson He | Resolved in planned debugging time in the iteration
34 | 5 | Bidding Cart Function | Changed UI to reflect that when round is closed, check out cannot occur. (viewMyCart.jsp) | Low | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
35 | 5 | View All Courses | Changed UI to reflect min. bid amt during round 2 in viewCourses.jsp | Low | 1 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
36 | 5 | View Bidding Results | Changed UI to reflect that bidding results can be viewed on user homepage (userHome.jsp) | Low | 1 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
37 | 5 | Bootstrap Function | Added method to clear minimum_bid table during bootstrap of new data | High | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
38 | 5 | Bootstrap Function | Debugged counting errors in bid.csv validation for bootstrap | High | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
39 | 5 | Bootstrap Function | Debugged invalid bid amount validation in bootstrap where correct decimal values are not inserted into database | High | 1 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
40 | 5 | Bootstrap Function | Debugged invalid section timetable clash bug to cater to validations of classes on Saturday and Sunday as well | High | 1 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
41 | 5 | Student Timetable Function | Changed UI for adminHome.jsp to allow admin to set start date of classes for student timetable | High | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
42 | 5 | View Bidding Results | Added min. bid column in bidding results page for user reference | Low | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
43 | 5 | Student Timetable Function | Created StudentTimetableDAO for CRUD purposes | High | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
44 | 5 | Student Timetable Function | Edited student Timetable controller to retrieve date of classes and support multiple users | High | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
45 | 5 | JSON section-dump | Renamed URL pattern for section_dump to section-dump | High | 5 |  | solved | 2016-02-11 | 2016-03-11 | Eugene Tan, Wilson He | Resolved in planned debugging time in the iteration
46 | 6 | JSON bid-status | Generate bid status when Round 1 has ended | Low | 5 | 20 | resolved | 2016-11-11 | 2016-12-11 | Yew Kit, Cristabel | Resolved in final test and debug on AWS session
47 | 6 | JSON bid-status | Generate bid status when Round 2 has ended(no bids placed) | Low | 5 |  | resolved | 2016-11-11 | 2016-12-11 | Yew Kit, Cristabel | Resolved in final test and debug on AWS session
48 | 6 | JSON bid-status | Generate bid status when Round 2 has ended(bids placed) | Low | 5 |  | resolved | 2016-11-11 | 2016-12-11 | Yew Kit, Cristabel | Resolved in final test and debug on AWS session
49 | 6 | Add to cart Function | Student could add to cart a session which exam clashed with current exam schedule | Low | 5 |  | resolved | 2016-11-12 | 2016-12-12 | Ming Kwang, Cristabel | Resolved in final test and debug on AWS session

## Bug Metric
Iteration | 1 | 2 | 3 | 4 | 5 | 6
Bug Metric Score | 0 | 16 | 28 | 33 | 56 | 20

## Mitigation Plan
Iteration | Task | Problem | Mitigation Plan
2 | Login/Logout & Search | Bug Metric > 10 | To schedule more time for debugging and testing for subsequent iterations
3 | Bidding Cart Function | Bug Metric > 10 | Run through corner cases carefully as a team before function development
4 | JSON functions | Bug Metric > 10 | Schedule more time for debugging depending on the complexity of the task itself - number of validations etc
5 | Regression testing/ Fixing Bugs that came out after Deployment on AWS | Bug Metric > 10 | Schedule some more time for debugging even after deployment as bugs came up after the deployment on AWS before UAT
6 | JSON Bid Status | Bug Metric > 10 | Bugs were a priority to continue solving during the final UAT testing and debugging session