## Pair Programming Log
PPM Formula | Estimated PP hours / Actual PP hours
| Number of tasks for Iteration 2 | 9
| Number of tasks for Iteration 3 | 36
| Number of tasks for Iteration 4 | 22
| Number of tasks for Iteration 5 | 14
| Number of tasks for Iteration 6 | 16
| Total Number of programming tasks | 97
Individual Programming Hours
Tan Ming Kwang | Cristabel Lau | Wilson He | Quek Yew Kit | Eugene Tan
94.69 | 98.51 | 95.05 | 94.12 | 96.01
Pair Programming Metrics
Iteration | Task | Estimated PP Hours | Actual PP Hours | Programmer 1 | Programmer 2 | PPM Metrics | Reason | Action Taken
2 | Create database in MySQL, database sql file and logic for Connection Manager function | 2 | 1.72 | Ming Kwang | Eugene Tan | 1.1628 | N/A | No Action Required
2 | Design UI for login form, home page and admin homepage | 1 | 0.88 | Ming Kwang | Eugene Tan | 1.1364 | N/A | No Action Required
2 | Develop logic for Login and Log out Function for both Student and Admin | 2 | 1.93 | Ming Kwang | Eugene Tan | 1.0363 | N/A | No Action Required
2 | Design UI for view all courses page | 1 | 0.97 | Cristabel Lau | Yew Kit | 1.0309 | N/A | No Action Required
2 | Develop logic for View All Courses Function | 2 | 2.4 | Cristabel Lau | Yew Kit | 0.83333 | N/A | No Action Required
2 | Testing and Debugging of Login/Logout Function with Test Cases | 1.5 | 0.45 | Ming Kwang | Eugene Tan | 3.3333 | Testing and debugging | No Action Required
2 | Develop logic for Search for a Course Function | 3 | 3.17 | Cristabel Lau | Yew Kit | 0.94637 | N/A | No Action Required
2 | Testing and Debugging View All Courses Function with Test Cases | 2 | 0.6 | Cristabel Lau | Yew Kit | 3.3333 | Testing and debugging | No Action Required
2 | Testing and Debugging Search for a Course Function with Test Cases | 2 | 1.17 | Cristabel Lau | Yew Kit | 1.7094 | Testing and debugging | No Action Required
3 | Design Bootstrap UI | 0.5 | 0.48 | Cristabel Lau | Wilson He | 1.0417 | N/A | No Action Required
3 | Develop Bidding Cart UI | 1 | 1.07 | Yew Kit | Eugene Tan | 0.93458 | N/A | No Action Required
3 | Develop Add to Cart, Delete from Cart | 3 | 3.03 | Yew Kit | Eugene Tan | 0.9901 | N/A | No Action Required
3 | Develop Upload and unzip function | 3 | 3.07 | Cristabel Lau | Wilson He | 0.9772 | N/A | No Action Required
3 | Debugging Upload and Unzip function | 2 | 1.95 | Cristabel Lau | Wilson He | 1.0256 | N/A | No Action Required
3 | Develop student.csv validation | 3 | 2.9 | Ming Kwang | Wilson He | 1.0345 | N/A | No Action Required
3 | Develop course.csv validation | 3 | 2.82 | Ming Kwang | Wilson He | 1.0638 | N/A | No Action Required
3 | Design Checkout UI | 1 | 1.05 | Yew Kit | Eugene Tan | 0.95238 | N/A | No Action Required
3 | Develop Checkout and Drop a Bid | 3 | 3.02 | Yew Kit | Eugene Tan | 0.99338 | N/A | No Action Required
3 | Develop section.csv validation | 3 | 3 | Cristabel Lau | Wilson He | 1 | N/A | No Action Required
3 | Develop prerequisite.csv validation | 3 | 2.98 | Ming Kwang | Wilson He | 1.0067 | N/A | No Action Required
3 | Develop bid.csv validation | 3 | 3.27 | Ming Kwang | Wilson He | 0.91743 | N/A | No Action Required
3 | Debugging of Bidding Cart function | 3 | 2.9 | Yew Kit | Eugene Tan | 1.0345 | N/A | No Action Required
3 | Debugging of student.csv validation | 3 | 0.32 | Ming Kwang | Wilson He | 9.375 | Testing and debugging | No Action Required
3 | Debugging of errors found during regression test | 4 | 3.95 | Wilson He | Eugene Tan | 1.0127 | N/A | No Action Required
3 | Debugging of course.csv validation | 3 | 0.4 | Ming Kwang | Cristabel Lau | 7.5 | Testing and debugging | No Action Required
3 | Develop course_completed.csv validation | 3 | 3.1 | Cristabel Lau | Wilson He | 0.96774 | N/A | No Action Required
3 | Debugging of prerequisite.csv validation | 3 | 0.02 | Ming Kwang | Cristabel Lau | 150 | Testing and debugging | No Action Required
3 | Debugging of section.csv validation | 3 | 0.2 | Cristabel Lau | Wilson He | 15 | Testing and debugging | No Action Required
3 | Design Start/Clearing Round UI | 1 | 1.57 | Ming Kwang | Cristabel Lau | 0.63694 | N/A | No Action Required
3 | Develop Start/Clearing Round Logic | 7 | 7.18 | Ming Kwang | Cristabel Lau | 0.97493 | N/A | No Action Required
3 | Debugging of bid.csv validation | 3 | 0.02 | Cristabel Lau | Wilson He | 150 | Testing and debugging | No Action Required
3 | Debugging of course_completed.csv validation | 3 | 1.43 | Cristabel Lau | Wilson He | 2.0979 | Testing and debugging | No Action Required
3 | Design UI for view student's enrolled course details and drop a section function | 3 | 2.98 | Yew Kit | Eugene Tan | 1.0067 | N/A | No Action Required
3 | Debugging of Start/Clearing Round Function | 2 | 2.22 | Ming Kwang | Cristabel Lau | 0.9009 | N/A | No Action Required
3 | Develop Error Log Function | 3 | 2.92 | Cristabel Lau | Wilson He | 1.0274 | N/A | No Action Required
3 | Develop Drop a Section Function | 3 | 2.28 | Yew Kit | Eugene Tan | 1.3158 | N/A | No Action Required
3 | Develop Insert function after validation is complete | 3 | 3.13 | Wilson He | Cristabel Lau | 0.95847 | N/A | No Action Required
3 | Develop View Student's Enrolled Course details function | 2 | 1.87 | Yew Kit | Eugene Tan | 1.0695 | N/A | No Action Required
3 | Debugging of Error Log Function | 2 | 0.87 | Cristabel Lau | Wilson He | 2.2989 | Testing and debugging | No Action Required
3 | Debugging of Drop a Section Function | 3 | 0.2 | Yew Kit | Eugene Tan | 15 | Testing and debugging | No Action Required
3 | Design UI of view bidding result | 1 | 1.07 | Cristabel Lau | Wilson He | 0.93458 | N/A | No Action Required
3 | Debugging of Insert Function after validation is complete | 1 | 0.38 | Cristabel Lau | Wilson He | 2.6316 | Testing and debugging | No Action Required
3 | Debug View Student's Enrolled Course Details function | 2 | 0.28 | Yew Kit | Eugene Tan | 7.1429 | Testing and debugging | No Action Required
3 | Develop View Bidding Result function | 3 | 4 | Cristabel Lau | Wilson He | 0.75 | N/A | No Action Required
3 | Debugging of View Bidding Result function | 2 | 1 | Cristabel Lau | Wilson He | 2 | Testing and debugging | No Action Required
4 | Develop Student Timetable Function | 2 | 2.47 | Yew Kit | Wilson He | 0.80972 | N/A | No Action Required
4 | Testing and debugging student timetable function | 1.5 | 2.02 | Yew Kit | Wilson He | 0.74257 | N/A | No Action Required
4 | Develop JSON authenticate web service | 1.5 | 1.52 | Ming Kwang | Cristabel Lau | 0.98684 | N/A | No Action Required
4 | Testing and debugging JSON authenticate web service | 1 | 0.35 | Ming Kwang | Cristabel Lau | 2.8571 | Testing and debugging | No Action Required
4 | Develop JSON delete bid web service | 2 | 2.17 | Yew Kit | Wilson He | 0.92166 | N/A | No Action Required
4 | Develop JSON drop section web service | 2 | 1.93 | Ming Kwang | Cristabel Lau | 1.0363 | N/A | No Action Required
4 | Develop JSON bootstrap web service | 6 | 5.93 | Ming Kwang | Cristabel Lau | 1.0118 | N/A | No Action Required
4 | Develop JSON dump (bid) web service | 3 | 2.83 | Yew Kit | Wilson He | 1.0601 | N/A | No Action Required
4 | Develop JSON dump (user) web service | 3 | 3.2 | Yew Kit | Wilson He | 0.9375 | N/A | No Action Required
4 | Testing and debugging JSON delete bid web service | 3 | 2.98 | Yew Kit | Wilson He | 1.0067 | N/A | No Action Required
4 | Testing and debugging JSON drop section web service | 3 | 0.58 | Ming Kwang | Cristabel Lau | 5.1724 | Testing and debugging | No Action Required
4 | Testing and debugging JSON bootstrap web service | 3 | 0.22 | Ming Kwang | Cristabel Lau | 13.6364 | Testing and debugging | No Action Required
4 | Testing and debugging JSON dump (user) web service | 3 | 1.87 | Yew Kit | Wilson He | 1.6043 | Testing and debugging | No Action Required
4 | Testing and debugging JSON dump (bid) web service | 3 | 2.53 | Yew Kit | Wilson He | 1.1858 | N/A | No Action Required
4 | Develop JSON dump table web service | 3 | 3.1 | Ming Kwang | Cristabel Lau | 0.96774 | N/A | No Action Required
4 | Develop JSON update bid web service | 3 | 2.82 | Yew Kit | Wilson He | 1.0638 | N/A | No Action Required
4 | Testing and debugging JSON dump table web service | 3 | 3.12 | Ming Kwang | Eugene Tan | 0.96154 | N/A | No Action Required
4 | Develop JSON dump (section) web service | 3 | 2.77 | Yew Kit | Wilson He | 1.083 | N/A | No Action Required
4 | Develop JSON start round web service | 3 | 2.93 | Ming Kwang | Cristabel Lau | 1.0239 | N/A | No Action Required
4 | Testing and debugging JSON dump (section) web service | 3 | 2.52 | Yew Kit | Wilson He | 1.1905 | N/A | No Action Required
4 | Testing and debugging JSON update bid web service | 1 | 1.77 | Yew Kit | Wilson He | 0.56497 | N/A | No Action Required
4 | Develop JSON stop round web service | 3 | 3.35 | Ming Kwang | Cristabel Lau | 0.89552 | N/A | No Action Required
5 | Testing and debugging for JSON Update Bid | 2 | 2.02 | Ming Kwang | Wilson He | 0.9901 | N/A | No Action Required
5 | Testing and debugging Search for a course function/view all courses and Login | 2 | 2.07 | Ming Kwang | Wilson He | 0.96618 | N/A | No Action Required
5 | Testing and debugging Bootstrap Function (Prereq / Course Completed / Bid / Insert Data) | 2 | 1.88 | Ming Kwang | Wilson He | 1.0638 | N/A | No Action Required
5 | Testing and debugging Bootstrap function (unzip / validation/ Course/ Section) Validation | 2 | 2.35 | Cristabel Lau | Eugene Tan | 0.85106 | N/A | No Action Required
5 | Testing and debugging Bid for Section / View Bidding Cart / Drop Bid / Start and End Round | 5 | 4.92 | Ming Kwang | Eugene Tan | 1.0163 | N/A | No Action Required
5 | Testing and debugging Drop Section, View Section / View Bidding Cart / View Bidding Results and JSON Login | 2 | 2.02 | Cristabel Lau | Eugene Tan | 0.9901 | N/A | No Action Required
5 | Testing and debugging JSON Bootstrap Function / Dump User / Dump Table | 5 | 5.22 | Ming Kwang | Eugene Tan | 0.95785 | N/A | No Action Required
5 | Testing and debugging JSON Drop Section / Delete Bid / Dump Bid | 2 | 2.05 | Ming Kwang | Wilson He | 0.97561 | N/A | No Action Required
5 | Testing and debugging JSON Dump Section / Start / Stop Round | 3 | 3.08 | Yew Kit | Eugene Tan | 0.97403 | N/A | No Action Required
5 | Testing and debugging Student Timetable and View Student Enrolled Courses | 3 | 2.97 | Yew Kit | Eugene Tan | 1.0101 | N/A | No Action Required
5 | Testing and debugging after deployment PAIR 1 | 5 | 4.95 | Ming Kwang | Eugene Tan | 1.0101 | N/A | No Action Required
5 | Testing and debugging after deployment PAIR 2 | 5 | 5.13 | Yew Kit | Eugene Tan | 0.97466 | N/A | No Action Required
5 | Testing and Debugging all functionalities - Fix functions that didn't pass UAT - PAIR 1 | 5 | 5.27 | Wilson He | Eugene Tan | 0.94877 | N/A | No Action Required
5 | Testing and Debugging all functionalities - Fix functions that didn't pass UAT - PAIR 2 | 5 | 4.92 | Yew Kit | Eugene Tan | 1.0163 | N/A | No Action Required
6 | Testing and debugging all bugs found in UAT (Auto) | 5 | 5.75 | Ming Kwang | Yew Kit | 0.86957 | N/A | No Action Required
6 | Testing and debugging all bugs found in UAT (Manual) | 3 | 3.42 | Cristabel Lau | Eugene Tan | 0.87719 | N/A | No Action Required
6 | Create Javadocs for Bootstrap student validation, section validation, prerequisite validation, course validation, bid validation | 3 | 3.93 | Ming Kwang | Cristabel Lau | 0.76336 | N/A | No Action Required
6 | Create Javadocs for DAO BidDAO, CourseDAO, LoginDAO, ConnectionManager | 2 | 2.52 | Yew Kit | Eugene Tan | 0.79365 | N/A | No Action Required
6 | Create Javadocs for Servlet AddToCartController, BidController, CheckOutCartController, DeleteFromCartController | 3 | 3.23 | Yew Kit | Eugene Tan | 0.92879 | N/A | No Action Required
6 | Create Javadocs for DAO SectionDAO, StudentDAO, StudentTimeTableDAO | 2 | 2.78 | Yew Kit | Eugene Tan | 0.71942 | N/A | No Action Required
6 | Develop JSON Function (Bid Status) | 3 | 3.22 | Cristabel Lau | Eugene Tan | 0.93168 | N/A | No Action Required
6 | Create Javadocs for Admin Utility, File Utility, Validation Utility, Course Bootstrap Completed Validation, DBController | 3 | 2.73 | Ming Kwang | Cristabel Lau | 1.0989 | N/A | No Action Required
6 | Create Javadocs for Entity Bid, Course, Section, ShoppingCart, ShoppingCartItem, Student, StudentTimeTable | 2 | 1.87 | Wilson He | Eugene Tan | 1.0695 | N/A | No Action Required
6 | Create Javadocs for Servlet DropBidController, DropSectionController, StudentTimeTableController, UploadController | 2 | 2 | Yew Kit | Cristabel Lau | 1 | N/A | No Action Required
6 | Create Javadocs for JSON login, dump user, dump table, start round, stop round, bootstrap | 3 | 3.25 | Wilson He | Eugene Tan | 0.92308 | N/A | No Action Required
6 | Create Javadocs for JSON update bid, delete bid, dump bid, drop section, dump section, Bid Status | 3 | 2.63 | Cristabel Lau | Eugene Tan | 1.1407 | N/A | No Action Required
6 | Create Javadocs for Servlet SearchController, StartRoundController, EndRoundController, LoginController, LogoutController | 3 | 2.3 | Yew Kit | Wilson He | 1.3043 | N/A | No Action Required
6 | Testing and debugging JSON Function (Bid Status) | 2 | 2.5 | Yew Kit | Cristabel Lau | 0.8 | N/A | No Action Required
6 | Develop updateSemStartDate, testing and debugging updateSemStartDate, and create Java Doc for updateSemStartController | 1.5 | 1.53 | Wilson He | Eugene Tan | 0.98039 | N/A | No Action Required
6 | Final Test/Debug on AWS | 6 | 7.48 | Ming Kwang | Cristabel Lau | 0.80214 | N/A | No Action Required

## Eugene Tan
Pair Programming Metrics
Iteration | Task | Estimated PP Hours | Actual PP Hours | Programmer 1 | Programmer 2 | PPM Metrics | Reason | Action Taken
2 | Create database in MySQL, database sql file and logic for Connection Manager function | 2 | 1.72 | Ming Kwang | Eugene Tan | 1.1628 | N/A | No Action Required
2 | Design UI for login form, home page and admin homepage | 1 | 0.88 | Ming Kwang | Eugene Tan | 1.1364 | N/A | No Action Required
2 | Develop logic for Login and Log out Function for both Student and Admin | 2 | 1.93 | Ming Kwang | Eugene Tan | 1.0363 | N/A | No Action Required
2 | Testing and Debugging of Login/Logout Function with Test Cases | 1.5 | 0.45 | Ming Kwang | Eugene Tan | 3.3333 | Testing and debugging | No Action Required
3 | Develop Bidding Cart UI | 1 | 1.07 | Yew Kit | Eugene Tan | 0.93458 | N/A | No Action Required
3 | Develop Add to Cart, Delete from Cart | 3 | 3.03 | Yew Kit | Eugene Tan | 0.9901 | N/A | No Action Required
3 | Design Checkout UI | 1 | 1.05 | Yew Kit | Eugene Tan | 0.95238 | N/A | No Action Required
3 | Develop Checkout and Drop a Bid | 3 | 3.02 | Yew Kit | Eugene Tan | 0.99338 | N/A | No Action Required
3 | Debugging of Bidding Cart function | 3 | 2.9 | Yew Kit | Eugene Tan | 1.0345 | N/A | No Action Required
3 | Debugging of errors found during regression test | 4 | 3.95 | Wilson He | Eugene Tan | 1.0127 | N/A | No Action Required
3 | Design UI for view student's enrolled course details and drop a section function | 3 | 2.98 | Yew Kit | Eugene Tan | 1.0067 | N/A | No Action Required
3 | Develop Drop a Section Function | 3 | 2.28 | Yew Kit | Eugene Tan | 1.3158 | N/A | No Action Required
3 | Develop View Student's Enrolled Course details function | 2 | 1.87 | Yew Kit | Eugene Tan | 1.0695 | N/A | No Action Required
3 | Debugging of Drop a Section Function | 3 | 0.2 | Yew Kit | Eugene Tan | 15 | Testing and debugging | No Action Required
3 | Debug View Student's Enrolled Course Details function | 2 | 0.28 | Yew Kit | Eugene Tan | 7.1429 | Testing and debugging | No Action Required
4 | Testing and debugging JSON dump table web service | 3 | 3.12 | Ming Kwang | Eugene Tan | 0.96154 | N/A | No Action Required
5 | Testing and debugging Bootstrap function (unzip / validation/ Course/ Section) Validation | 2 | 2.35 | Cristabel Lau | Eugene Tan | 0.85106 | N/A | No Action Required
5 | Testing and debugging Bid for Section / View Bidding Cart / Drop Bid / Start and End Round | 5 | 4.92 | Ming Kwang | Eugene Tan | 1.0163 | N/A | No Action Required
5 | Testing and debugging Drop Section, View Section / View Bidding Cart / View Bidding Results and JSON Login | 2 | 2.02 | Cristabel Lau | Eugene Tan | 0.9901 | N/A | No Action Required
5 | Testing and debugging JSON Bootstrap Function / Dump User / Dump Table | 5 | 5.22 | Ming Kwang | Eugene Tan | 0.95785 | N/A | No Action Required
5 | Testing and debugging JSON Dump Section / Start / Stop Round | 3 | 3.08 | Yew Kit | Eugene Tan | 0.97403 | N/A | No Action Required
5 | Testing and debugging Student Timetable and View Student Enrolled Courses | 3 | 2.97 | Yew Kit | Eugene Tan | 1.0101 | N/A | No Action Required
5 | Testing and debugging after deployment PAIR 1 | 5 | 4.95 | Ming Kwang | Eugene Tan | 1.0101 | N/A | No Action Required
5 | Testing and debugging after deployment PAIR 2 | 5 | 5.13 | Yew Kit | Eugene Tan | 0.97466 | N/A | No Action Required
5 | Testing and Debugging all functionalities - Fix functions that didn't pass UAT - PAIR 1 | 5 | 5.27 | Wilson He | Eugene Tan | 0.94877 | N/A | No Action Required
5 | Testing and Debugging all functionalities - Fix functions that didn't pass UAT - PAIR 2 | 5 | 4.92 | Yew Kit | Eugene Tan | 1.0163 | N/A | No Action Required
6 | Testing and debugging all bugs found in UAT (Manual) | 3 | 3.42 | Cristabel Lau | Eugene Tan | 0.87719 | N/A | No Action Required
6 | Create Javadocs for DAO BidDAO, CourseDAO, LoginDAO, ConnectionManager | 2 | 2.52 | Yew Kit | Eugene Tan | 0.79365 | N/A | No Action Required
6 | Create Javadocs for Servlet AddToCartController, BidController, CheckOutCartController, DeleteFromCartController | 3 | 3.23 | Yew Kit | Eugene Tan | 0.92879 | N/A | No Action Required
6 | Create Javadocs for DAO SectionDAO, StudentDAO, StudentTimeTableDAO | 2 | 2.78 | Yew Kit | Eugene Tan | 0.71942 | N/A | No Action Required
6 | Develop JSON Function (Bid Status) | 3 | 3.22 | Cristabel Lau | Eugene Tan | 0.93168 | N/A | No Action Required
6 | Create Javadocs for Entity Bid, Course, Section, ShoppingCart, ShoppingCartItem, Student, StudentTimeTable | 2 | 1.87 | Wilson He | Eugene Tan | 1.0695 | N/A | No Action Required
6 | Create Javadocs for JSON login, dump user, dump table, start round, stop round, bootstrap | 3 | 3.25 | Wilson He | Eugene Tan | 0.92308 | N/A | No Action Required
6 | Create Javadocs for JSON update bid, delete bid, dump bid, drop section, dump section, Bid Status | 3 | 2.63 | Cristabel Lau | Eugene Tan | 1.1407 | N/A | No Action Required
6 | Develop updateSemStartDate, testing and debugging updateSemStartDate, and create Java Doc for updateSemStartController | 1.5 | 1.53 | Wilson He | Eugene Tan | 0.98039 | N/A | No Action Required
Tasks by Iteration
| Number of Tasks for Iteration 2 | 4
| Number of Tasks for Iteration 3 | 11
| Number of Tasks for Iteration 4 | 1
| Number of Tasks for Iteration 5 | 10
| Number of Tasks for Iteration 6 | 9
| Total Number of Tasks | 35
Pair Programming Hours by Iteration
| Iteration 2 PP Hours | 4.98
| Iteration 3 PP Hours | 22.63
| Iteration 4 PP Hours | 3.12
| Iteration 5 PP Hours | 40.83
| Iteration 6 PP Hours | 24.45
| Total PP Hours | 96.01

## Tan Ming Kwang
Pair Programming Metrics
Iteration | Task | Estimated PP Hours | Actual PP Hours | Programmer 1 | Programmer 2 | PPM Metrics | Reason | Action Taken
2 | Create database in MySQL, database sql file and logic for Connection Manager function | 2 | 1.72 | Ming Kwang | Eugene Tan | 1.1628 | N/A | No Action Required
2 | Design UI for login form, home page and admin homepage | 1 | 0.88 | Ming Kwang | Eugene Tan | 1.1364 | N/A | No Action Required
2 | Develop logic for Login and Log out Function for both Student and Admin | 2 | 1.93 | Ming Kwang | Eugene Tan | 1.0363 | N/A | No Action Required
2 | Testing and Debugging of Login/Logout Function with Test Cases | 1.5 | 0.45 | Ming Kwang | Eugene Tan | 3.3333 | Testing and debugging | No Action Required
3 | Develop student.csv validation | 3 | 2.9 | Ming Kwang | Wilson He | 1.0345 | N/A | No Action Required
3 | Develop course.csv validation | 3 | 2.82 | Ming Kwang | Wilson He | 1.0638 | N/A | No Action Required
3 | Develop prerequisite.csv validation | 3 | 2.98 | Ming Kwang | Wilson He | 1.0067 | N/A | No Action Required
3 | Develop bid.csv validation | 3 | 3.27 | Ming Kwang | Wilson He | 0.91743 | N/A | No Action Required
3 | Debugging of student.csv validation | 3 | 0.32 | Ming Kwang | Wilson He | 9.375 | Testing and debugging | No Action Required
3 | Debugging of course.csv validation | 3 | 0.4 | Ming Kwang | Cristabel Lau | 7.5 | Testing and debugging | No Action Required
3 | Debugging of prerequisite.csv validation | 3 | 0.02 | Ming Kwang | Cristabel Lau | 150 | Testing and debugging | No Action Required
3 | Design Start/Clearing Round UI | 1 | 1.57 | Ming Kwang | Cristabel Lau | 0.63694 | N/A | No Action Required
3 | Develop Start/Clearing Round Logic | 7 | 7.18 | Ming Kwang | Cristabel Lau | 0.97493 | N/A | No Action Required
3 | Debugging of Start/Clearing Round Function | 2 | 2.22 | Ming Kwang | Cristabel Lau | 0.9009 | N/A | No Action Required
4 | Develop JSON authenticate web service | 1.5 | 1.52 | Ming Kwang | Cristabel Lau | 0.98684 | N/A | No Action Required
4 | Testing and debugging JSON authenticate web service | 1 | 0.35 | Ming Kwang | Cristabel Lau | 2.8571 | Testing and debugging | No Action Required
4 | Develop JSON drop section web service | 2 | 1.93 | Ming Kwang | Cristabel Lau | 1.0363 | N/A | No Action Required
4 | Develop JSON bootstrap web service | 6 | 5.93 | Ming Kwang | Cristabel Lau | 1.0118 | N/A | No Action Required
4 | Testing and debugging JSON drop section web service | 3 | 0.58 | Ming Kwang | Cristabel Lau | 5.1724 | Testing and debugging | No Action Required
4 | Testing and debugging JSON bootstrap web service | 3 | 0.22 | Ming Kwang | Cristabel Lau | 13.6364 | Testing and debugging | No Action Required
4 | Develop JSON dump table web service | 3 | 3.1 | Ming Kwang | Cristabel Lau | 0.96774 | N/A | No Action Required
4 | Testing and debugging JSON dump table web service | 3 | 3.12 | Ming Kwang | Eugene Tan | 0.96154 | N/A | No Action Required
4 | Develop JSON start round web service | 3 | 2.93 | Ming Kwang | Cristabel Lau | 1.0239 | N/A | No Action Required
4 | Develop JSON stop round web service | 3 | 3.35 | Ming Kwang | Cristabel Lau | 0.89552 | N/A | No Action Required
5 | Testing and debugging for JSON Update Bid | 2 | 2.02 | Ming Kwang | Wilson He | 0.9901 | N/A | No Action Required
5 | Testing and debugging Search for a course function/view all courses and Login | 2 | 2.07 | Ming Kwang | Wilson He | 0.96618 | N/A | No Action Required
5 | Testing and debugging Bootstrap Function (Prereq / Course Completed / Bid / Insert Data) | 2 | 1.88 | Ming Kwang | Wilson He | 1.0638 | N/A | No Action Required
5 | Testing and debugging Bid for Section / View Bidding Cart / Drop Bid / Start and End Round | 5 | 4.92 | Ming Kwang | Eugene Tan | 1.0163 | N/A | No Action Required
5 | Testing and debugging JSON Bootstrap Function / Dump User / Dump Table | 5 | 5.22 | Ming Kwang | Eugene Tan | 0.95785 | N/A | No Action Required
5 | Testing and debugging JSON Drop Section / Delete Bid / Dump Bid | 2 | 2.05 | Ming Kwang | Wilson He | 0.97561 | N/A | No Action Required
5 | Testing and debugging after deployment PAIR 1 | 5 | 4.95 | Ming Kwang | Eugene Tan | 1.0101 | N/A | No Action Required
6 | Testing and debugging all bugs found in UAT (Auto) | 5 | 5.75 | Ming Kwang | Yew Kit | 0.86957 | N/A | No Action Required
6 | Create Javadocs for Bootstrap student validation, section validation, prerequisite validation, course validation, bid validation | 3 | 3.93 | Ming Kwang | Wilson He | 0.76336 | N/A | No Action Required
6 | Create Javadocs for Admin Utility, File Utility, Validation Utility, Course Bootstrap Completed Validation, DBController | 3 | 2.73 | Ming Kwang | Cristabel Lau | 1.0989 | N/A | No Action Required
6 | Final Test/Debug on AWS | 6 | 7.48 | Ming Kwang | Cristabel Lau | 0.80214 | N/A | No Action Required
Tasks by Iteration
| Number of Tasks for Iteration 2 | 4
| Number of Tasks for Iteration 3 | 10
| Number of Tasks for Iteration 4 | 10
| Number of Tasks for Iteration 5 | 7
| Number of Tasks for Iteration 6 | 4
| Total Number of Tasks | 35
Pair Programming Hours by Iteration
| Iteration 2 PP Hours | 4.98
| Iteration 3 PP Hours | 23.68
| Iteration 4 PP Hours | 23.03
| Iteration 5 PP Hours | 23.11
| Iteration 6 PP Hours | 19.89
| Total PP Hours | 94.69

## Cristabel Lau
Pair Programming Metrics
Iteration | Task | Estimated PP Hours | Actual PP Hours | Programmer 1 | Programmer 2 | PPM Metrics | Reason | Action Taken
2 | Design UI for view all courses page | 1 | 0.97 | Cristabel Lau | Yew Kit | 1.0309 | N/A | No Action Required
2 | Develop logic for View All Courses Function | 2 | 2.4 | Cristabel Lau | Yew Kit | 0.83333 | N/A | No Action Required
2 | Develop logic for Search for a Course Function | 3 | 3.17 | Cristabel Lau | Yew Kit | 0.94637 | N/A | No Action Required
2 | Testing and Debugging View All Courses Function with Test Cases | 2 | 0.6 | Cristabel Lau | Yew Kit | 3.3333 | Testing and debugging | No Action Required
2 | Testing and Debugging Search for a Course Function with Test Cases | 2 | 1.17 | Cristabel Lau | Yew Kit | 1.7094 | Testing and debugging | No Action Required
3 | Design Bootstrap UI | 0.5 | 0.48 | Cristabel Lau | Wilson He | 1.0417 | N/A | No Action Required
3 | Develop Upload and unzip function | 3 | 3.07 | Cristabel Lau | Wilson He | 0.9772 | N/A | No Action Required
3 | Debugging Upload and Unzip function | 2 | 1.95 | Cristabel Lau | Wilson He | 1.0256 | N/A | No Action Required
3 | Develop section.csv validation | 3 | 3 | Cristabel Lau | Wilson He | 1 | N/A | No Action Required
3 | Debugging of course.csv validation | 3 | 0.4 | Ming Kwang | Cristabel Lau | 7.5 | Testing and debugging | No Action Required
3 | Develop course_completed.csv validation | 3 | 3.1 | Cristabel Lau | Wilson He | 0.96774 | N/A | No Action Required
3 | Debugging of prerequisite.csv validation | 3 | 0.02 | Ming Kwang | Cristabel Lau | 150 | Testing and debugging | No Action Required
3 | Debugging of section.csv validation | 3 | 0.2 | Cristabel Lau | Wilson He | 15 | Testing and debugging | No Action Required
3 | Design Start/Clearing Round UI | 1 | 1.57 | Ming Kwang | Cristabel Lau | 0.63694 | N/A | No Action Required
3 | Develop Start/Clearing Round Logic | 7 | 7.18 | Ming Kwang | Cristabel Lau | 0.97493 | N/A | No Action Required
3 | Debugging of bid.csv validation | 3 | 0.02 | Cristabel Lau | Wilson He | 150 | Testing and debugging | No Action Required
3 | Debugging of course_completed.csv validation | 3 | 1.43 | Cristabel Lau | Wilson He | 2.0979 | Testing and debugging | No Action Required
3 | Debugging of Start/Clearing Round Function | 2 | 2.22 | Ming Kwang | Cristabel Lau | 0.9009 | N/A | No Action Required
3 | Develop Error Log Function | 3 | 2.92 | Cristabel Lau | Wilson He | 1.0274 | N/A | No Action Required
3 | Develop Insert function after validation is complete | 3 | 3.13 | Wilson He | Cristabel Lau | 0.95847 | N/A | No Action Required
3 | Debugging of Error Log Function | 2 | 0.87 | Cristabel Lau | Wilson He | 2.2989 | Testing and debugging | No Action Required
3 | Design UI of view bidding result | 1 | 1.07 | Cristabel Lau | Wilson He | 0.93458 | N/A | No Action Required
3 | Debugging of Insert Function after validation is complete | 1 | 0.38 | Cristabel Lau | Wilson He | 2.6316 | Testing and debugging | No Action Required
3 | Develop View Bidding Result function | 3 | 4 | Cristabel Lau | Wilson He | 0.75 | N/A | No Action Required
3 | Debugging of View Bidding Result function | 2 | 1 | Cristabel Lau | Wilson He | 2 | Testing and debugging | No Action Required
4 | Develop JSON authenticate web service | 1.5 | 1.52 | Ming Kwang | Cristabel Lau | 0.98684 | N/A | No Action Required
4 | Testing and debugging JSON authenticate web service | 1 | 0.35 | Ming Kwang | Cristabel Lau | 2.8571 | Testing and debugging | No Action Required
4 | Develop JSON drop section web service | 2 | 1.93 | Ming Kwang | Cristabel Lau | 1.0363 | N/A | No Action Required
4 | Develop JSON bootstrap web service | 6 | 5.93 | Ming Kwang | Cristabel Lau | 1.0118 | N/A | No Action Required
4 | Testing and debugging JSON drop section web service | 3 | 0.58 | Ming Kwang | Cristabel Lau | 5.1724 | Testing and debugging | No Action Required
4 | Testing and debugging JSON bootstrap web service | 3 | 0.22 | Ming Kwang | Cristabel Lau | 13.6364 | Testing and debugging | No Action Required
4 | Develop JSON dump table web service | 3 | 3.1 | Ming Kwang | Cristabel Lau | 0.96774 | N/A | No Action Required
4 | Develop JSON start round web service | 3 | 2.93 | Ming Kwang | Cristabel Lau | 1.0239 | N/A | No Action Required
4 | Develop JSON stop round web service | 3 | 3.35 | Ming Kwang | Cristabel Lau | 0.89552 | N/A | No Action Required
5 | Testing and debugging Bootstrap function (unzip / validation/ Course/ Section) Validation | 2 | 2.35 | Cristabel Lau | Eugene Tan | 0.85106 | N/A | No Action Required
5 | Testing and debugging Drop Section, View Section / View Bidding Cart / View Bidding Results and JSON Login | 2 | 2.02 | Cristabel Lau | Eugene Tan | 0.9901 | N/A | No Action Required
6 | Testing and debugging all bugs found in UAT (Manual) | 3 | 3.42 | Cristabel Lau | Eugene Tan | 0.87719 | N/A | No Action Required
6 | Create Javadocs for Bootstrap student validation, section validation, prerequisite validation, course validation, bid validation | 3 | 3.93 | Ming Kwang | Cristabel Lau | 0.76336 | N/A | No Action Required
6 | Develop JSON Function (Bid Status) | 3 | 3.22 | Cristabel Lau | Eugene Tan | 0.93168 | N/A | No Action Required
6 | Create Javadocs for Admin Utility, File Utility, Validation Utility, Course Bootstrap Completed Validation, DBController | 3 | 2.73 | Ming Kwang | Cristabel Lau | 1.0989 | N/A | No Action Required
6 | Create Javadocs for Servlet DropBidController, DropSectionController, StudentTimeTableController, UploadController | 2 | 2 | Yew Kit | Cristabel Lau | 1 | N/A | No Action Required
6 | Create Javadocs for JSON update bid, delete bid, dump bid, drop section, dump section, Bid Status | 3 | 2.63 | Cristabel Lau | Eugene Tan | 1.1407 | N/A | No Action Required
6 | Testing and debugging JSON Function (Bid Status) | 2 | 2.5 | Yew Kit | Cristabel Lau | 0.8 | N/A | No Action Required
6 | Final Test/Debug on AWS | 6 | 7.48 | Ming Kwang | Cristabel Lau | 0.80214 | N/A | No Action Required
Tasks by Iteration
| Number of Tasks for Iteration 2 | 5
| Number of Tasks for Iteration 3 | 20
| Number of Tasks for Iteration 4 | 9
| Number of Tasks for Iteration 5 | 2
| Number of Tasks for Iteration 6 | 8
| Total Number of Tasks | 44
Pair Programming Hours by Iteration
| Iteration 2 PP Hours | 8.31
| Iteration 3 PP Hours | 38.01
| Iteration 4 PP Hours | 19.91
| Iteration 5 PP Hours | 4.37
| Iteration 6 PP Hours | 27.91
| Total PP Hours | 98.51

## Quek Yew Kit
Pair Programming Metrics
Iteration | Task | Estimated PP Hours | Actual PP Hours | Programmer 1 | Programmer 2 | PPM Metrics | Reason | Action Taken
2 | Design UI for view all courses page | 1 | 0.97 | Cristabel Lau | Yew Kit | 1.0309 | N/A | No Action Required
2 | Develop logic for View All Courses Function | 2 | 2.4 | Cristabel Lau | Yew Kit | 0.83333 | N/A | No Action Required
2 | Develop logic for Search for a Course Function | 3 | 3.17 | Cristabel Lau | Yew Kit | 0.94637 | N/A | No Action Required
2 | Testing and Debugging View All Courses Function with Test Cases | 2 | 0.6 | Cristabel Lau | Yew Kit | 3.3333 | Testing and debugging | No Action Required
2 | Testing and Debugging Search for a Course Function with Test Cases | 2 | 1.17 | Cristabel Lau | Yew Kit | 1.7094 | Testing and debugging | No Action Required
3 | Develop Bidding Cart UI | 1 | 1.07 | Yew Kit | Eugene Tan | 0.93458 | N/A | No Action Required
3 | Develop Add to Cart, Delete from Cart | 3 | 3.03 | Yew Kit | Eugene Tan | 0.9901 | N/A | No Action Required
3 | Design Checkout UI | 1 | 1.05 | Yew Kit | Eugene Tan | 0.95238 | N/A | No Action Required
3 | Develop Checkout and Drop a Bid | 3 | 3.02 | Yew Kit | Eugene Tan | 0.99338 | N/A | No Action Required
3 | Debugging of Bidding Cart function | 3 | 2.9 | Yew Kit | Eugene Tan | 1.0345 | N/A | No Action Required
3 | Design UI for view student's enrolled course details and drop a section function | 3 | 2.98 | Yew Kit | Eugene Tan | 1.0067 | N/A | No Action Required
3 | Develop Drop a Section Function | 3 | 2.28 | Yew Kit | Eugene Tan | 1.3158 | N/A | No Action Required
3 | Develop View Student's Enrolled Course details function | 2 | 1.87 | Yew Kit | Eugene Tan | 1.0695 | N/A | No Action Required
3 | Debugging of Drop a Section Function | 3 | 0.2 | Yew Kit | Eugene Tan | 15 | Testing and debugging | No Action Required
3 | Debug View Student's Enrolled Course Details function | 2 | 0.28 | Yew Kit | Eugene Tan | 7.1429 | Testing and debugging | No Action Required
4 | Develop Student Timetable Function | 2 | 2.47 | Yew Kit | Wilson He | 0.80972 | N/A | No Action Required
4 | Testing and debugging student timetable function | 1.5 | 2.02 | Yew Kit | Wilson He | 0.74257 | N/A | No Action Required
4 | Develop JSON delete bid web service | 2 | 2.17 | Yew Kit | Wilson He | 0.92166 | N/A | No Action Required
4 | Develop JSON dump (bid) web service | 3 | 2.83 | Yew Kit | Wilson He | 1.0601 | N/A | No Action Required
4 | Develop JSON dump (user) web service | 3 | 3.2 | Yew Kit | Wilson He | 0.9375 | N/A | No Action Required
4 | Testing and debugging JSON delete bid web service | 3 | 2.98 | Yew Kit | Wilson He | 1.0067 | N/A | No Action Required
4 | Testing and debugging JSON dump (user) web service | 3 | 1.87 | Yew Kit | Wilson He | 1.6043 | Testing and debugging | No Action Required
4 | Testing and debugging JSON dump (bid) web service | 3 | 2.53 | Yew Kit | Wilson He | 1.1858 | N/A | No Action Required
4 | Develop JSON update bid web service | 3 | 2.82 | Yew Kit | Wilson He | 1.0638 | N/A | No Action Required
4 | Develop JSON dump (section) web service | 3 | 2.77 | Yew Kit | Wilson He | 1.083 | N/A | No Action Required
4 | Testing and debugging JSON dump (section) web service | 3 | 2.52 | Yew Kit | Wilson He | 1.1905 | N/A | No Action Required
4 | Testing and debugging JSON update bid web service | 1 | 1.77 | Yew Kit | Wilson He | 0.56497 | N/A | No Action Required
5 | Testing and debugging JSON Dump Section / Start / Stop Round | 3 | 3.08 | Yew Kit | Eugene Tan | 0.97403 | N/A | No Action Required
5 | Testing and debugging Student Timetable and View Student Enrolled Courses | 3 | 2.97 | Yew Kit | Eugene Tan | 1.0101 | N/A | No Action Required
5 | Testing and debugging after deployment PAIR 2 | 5 | 5.13 | Yew Kit | Eugene Tan | 0.97466 | N/A | No Action Required
5 | Testing and Debugging all functionalities - Fix functions that didn't pass UAT - PAIR 2 | 5 | 4.92 | Yew Kit | Eugene Tan | 1.0163 | N/A | No Action Required
6 | Testing and debugging all bugs found in UAT (Auto) | 5 | 5.75 | Ming Kwang | Yew Kit | 0.86957 | N/A | No Action Required
6 | Create Javadocs for DAO BidDAO, CourseDAO, LoginDAO, ConnectionManager | 2 | 2.52 | Yew Kit | Eugene Tan | 0.79365 | N/A | No Action Required
6 | Create Javadocs for Servlet AddToCartController, BidController, CheckOutCartController, DeleteFromCartController | 3 | 3.23 | Yew Kit | Eugene Tan | 0.92879 | N/A | No Action Required
6 | Create Javadocs for DAO SectionDAO, StudentDAO, StudentTimeTableDAO | 2 | 2.78 | Yew Kit | Eugene Tan | 0.71942 | N/A | No Action Required
6 | Create Javadocs for Servlet DropBidController, DropSectionController, StudentTimeTableController, UploadController | 2 | 2 | Yew Kit | Cristabel Lau | 1 | N/A | No Action Required
6 | Create Javadocs for Servlet SearchController, StartRoundController, EndRoundController, LoginController, LogoutController | 3 | 2.3 | Yew Kit | Wilson He | 1.3043 | N/A | No Action Required
6 | Testing and debugging JSON Function (Bid Status) | 2 | 2.5 | Yew Kit | Cristabel Lau | 0.8 | N/A | No Action Required
Tasks by Iteration
| Number of Tasks for Iteration 2 | 5
| Number of Tasks for Iteration 3 | 10
| Number of Tasks for Iteration 4 | 12
| Number of Tasks for Iteration 5 | 4
| Number of Tasks for Iteration 6 | 7
| Total Number of Tasks | 38
Pair Programming Hours by Iteration
| Iteration 2 PP Hours | 8.31
| Iteration 3 PP Hours | 18.68
| Iteration 4 PP Hours | 29.95
| Iteration 5 PP Hours | 16.1
| Iteration 6 PP Hours | 21.08
| Total PP Hours | 94.12

## Wilson He
Pair Programming Metrics
Iteration | Task | Estimated PP Hours | Actual PP Hours | Programmer 1 | Programmer 2 | PPM Metrics | Reason | Action Taken
3 | Design Bootstrap UI | 0.5 | 0.48 | Cristabel Lau | Wilson He | 1.0417 | N/A | No Action Required
3 | Develop Upload and unzip function | 3 | 3.07 | Cristabel Lau | Wilson He | 0.9772 | N/A | No Action Required
3 | Debugging Upload and Unzip function | 2 | 1.95 | Cristabel Lau | Wilson He | 1.0256 | N/A | No Action Required
3 | Develop student.csv validation | 3 | 2.9 | Ming Kwang | Wilson He | 1.0345 | N/A | No Action Required
3 | Develop course.csv validation | 3 | 2.82 | Ming Kwang | Wilson He | 1.0638 | N/A | No Action Required
3 | Develop section.csv validation | 3 | 3 | Cristabel Lau | Wilson He | 1 | N/A | No Action Required
3 | Develop prerequisite.csv validation | 3 | 2.98 | Ming Kwang | Wilson He | 1.0067 | N/A | No Action Required
3 | Develop bid.csv validation | 3 | 3.27 | Ming Kwang | Wilson He | 0.91743 | N/A | No Action Required
3 | Debugging of student.csv validation | 3 | 0.32 | Ming Kwang | Wilson He | 9.375 | Testing and debugging | No Action Required
3 | Debugging of errors found during regression test | 4 | 3.95 | Wilson He | Eugene Tan | 1.0127 | N/A | No Action Required
3 | Develop course_completed.csv validation | 3 | 3.1 | Cristabel Lau | Wilson He | 0.96774 | N/A | No Action Required
3 | Debugging of section.csv validation | 3 | 0.2 | Cristabel Lau | Wilson He | 15 | Testing and debugging | No Action Required
3 | Debugging of bid.csv validation | 3 | 0.02 | Cristabel Lau | Wilson He | 150 | Testing and debugging | No Action Required
3 | Debugging of course_completed.csv validation | 3 | 1.43 | Cristabel Lau | Wilson He | 2.0979 | Testing and debugging | No Action Required
3 | Develop Error Log Function | 3 | 2.92 | Cristabel Lau | Wilson He | 1.0274 | N/A | No Action Required
3 | Develop Insert function after validation is complete | 3 | 3.13 | Wilson He | Cristabel Lau | 0.95847 | N/A | No Action Required
3 | Debugging of Error Log Function | 2 | 0.87 | Cristabel Lau | Wilson He | 2.2989 | Testing and debugging | No Action Required
3 | Design UI of view bidding result | 1 | 1.07 | Cristabel Lau | Wilson He | 0.93458 | N/A | No Action Required
3 | Debugging of Insert Function after validation is complete | 1 | 0.38 | Cristabel Lau | Wilson He | 2.6316 | Testing and debugging | No Action Required
3 | Develop View Bidding Result function | 3 | 4 | Cristabel Lau | Wilson He | 0.75 | N/A | No Action Required
3 | Debugging of View Bidding Result function | 2 | 1 | Cristabel Lau | Wilson He | 2 | Testing and debugging | No Action Required
4 | Develop Student Timetable Function | 2 | 2.47 | Yew Kit | Wilson He | 0.80972 | N/A | No Action Required
4 | Testing and debugging student timetable function | 1.5 | 2.02 | Yew Kit | Wilson He | 0.74257 | N/A | No Action Required
4 | Develop JSON delete bid web service | 2 | 2.17 | Yew Kit | Wilson He | 0.92166 | N/A | No Action Required
4 | Develop JSON dump (bid) web service | 3 | 2.83 | Yew Kit | Wilson He | 1.0601 | N/A | No Action Required
4 | Develop JSON dump (user) web service | 3 | 3.2 | Yew Kit | Wilson He | 0.9375 | N/A | No Action Required
4 | Testing and debugging JSON delete bid web service | 3 | 2.98 | Yew Kit | Wilson He | 1.0067 | N/A | No Action Required
4 | Testing and debugging JSON dump (user) web service | 3 | 1.87 | Yew Kit | Wilson He | 1.6043 | Testing and debugging | No Action Required
4 | Testing and debugging JSON dump (bid) web service | 3 | 2.53 | Yew Kit | Wilson He | 1.1858 | N/A | No Action Required
4 | Develop JSON update bid web service | 3 | 2.82 | Yew Kit | Wilson He | 1.0638 | N/A | No Action Required
4 | Develop JSON dump (section) web service | 3 | 2.77 | Yew Kit | Wilson He | 1.083 | N/A | No Action Required
4 | Testing and debugging JSON dump (section) web service | 3 | 2.52 | Yew Kit | Wilson He | 1.1905 | N/A | No Action Required
4 | Testing and debugging JSON update bid web service | 1 | 1.77 | Yew Kit | Wilson He | 0.56497 | N/A | No Action Required
5 | Testing and debugging for JSON Update Bid | 2 | 2.02 | Ming Kwang | Wilson He | 0.9901 | N/A | No Action Required
5 | Testing and debugging Search for a course function/view all courses and Login | 2 | 2.07 | Ming Kwang | Wilson He | 0.96618 | N/A | No Action Required
5 | Testing and debugging Bootstrap Function (Prereq / Course Completed / Bid / Insert Data) | 2 | 1.88 | Ming Kwang | Wilson He | 1.0638 | N/A | No Action Required
5 | Testing and debugging JSON Drop Section / Delete Bid / Dump Bid | 2 | 2.05 | Ming Kwang | Wilson He | 0.97561 | N/A | No Action Required
5 | Testing and Debugging all functionalities - Fix functions that didn't pass UAT - PAIR 1 | 5 | 5.27 | Wilson He | Eugene Tan | 0.94877 | N/A | No Action Required
6 | Create Javadocs for Entity Bid, Course, Section, ShoppingCart, ShoppingCartItem, Student, StudentTimeTable | 2 | 1.87 | Wilson He | Eugene Tan | 1.0695 | N/A | No Action Required
6 | Create Javadocs for JSON login, dump user, dump table, start round, stop round, bootstrap | 3 | 3.25 | Wilson He | Eugene Tan | 0.92308 | N/A | No Action Required
6 | Create Javadocs for Servlet SearchController, StartRoundController, EndRoundController, LoginController, LogoutController | 3 | 2.3 | Yew Kit | Wilson He | 1.3043 | N/A | No Action Required
6 | Develop updateSemStartDate, testing and debugging updateSemStartDate, and create Java Doc for updateSemStartController | 1.5 | 1.53 | Wilson He | Eugene Tan | 0.98039 | N/A | No Action Required
Tasks by Iteration
| Number of Tasks for Iteration 3 | 21
| Number of Tasks for Iteration 4 | 12
| Number of Tasks for Iteration 5 | 5
| Number of Tasks for Iteration 6 | 4
| Total Number of Tasks | 42
Pair Programming Hours by Iteration
| Iteration 3 PP Hours | 42.86
| Iteration 4 PP Hours | 29.95
| Iteration 5 PP Hours | 13.29
| Iteration 6 PP Hours | 8.95
| Total PP Hours | 95.05