## Slide 1: PM Review G6T3 No Weekends
Tan Ming Kwang (Project Manager)
Wilson He
Cristabel Lau
Eugene Tan
Quek Yew Kit

## Slide 2: Agenda
Functionalities
Schedule
Critical Path
Metrics
Mitigation Plan
Roles & Responsibilities
Rotation Schedule

## Slide 3: Functionalities
Functions
Login/Logout
View / Search for Courses
Bidding Cart (add / delete / check out)
Drop a Bid
View student enrolled course
Drop a section
Bootstrap (unzip, validation, insert, error log)
Start / End Round (Clearing round)
View Bidding Results
Student Timetable
Not dropping any functionalities
Adding: Bidding Cart, Student Timetable
Architecture: MVC

## Slide 4: Schedule
Iteration | Week(s) | Start Date | End Date | Functions | Milestone
Iteration 1 | 5 | 12/9/2016 | 18/9/2016 | Planning Diagrams | 
Iteration 2 | 6 | 19/9/2016 | 25/9/2016 | DB Setup Login / Logout View Courses Search Courses | Supervisor Meeting 1
Iteration 3 | 7, 8 | 26/9/2016 | 9/10/2016 | Week 7 Bootstrap Bidding Cart (CRUD cart, check out) Drop a bid Week 8 Bootstrap View student enrolled course Drop a section Start / End Round View Bidding Results | PM Review (Week 7)

## Slide 5: Schedule
Iteration | Week(s) | Start Date | End Date | Functions | Milestone
Iteration 4 | 9, 10 | 10/10/2016 | 23/10/2016 | JSON Web Service Java Docs Student Timetable | Application Demo (Week 9)
Iteration 5 | 11, 12 | 24/10/2016 | 6/11/2016 | Buffer Week for Testing and Debugging | Supervisor Meeting 2 (Week 11) UAT (Week 12)
Iteration 6 | 13, 14 | 7/11/2016 | 13/11/2016 | Testing and Debugging | Final Presentation (Week 14)

## Slide 6: Task Assignment
Tasks | Wilson | Ming Kwang | Eugene | Yew Kit | Cristabel
Login/Logout |  |  |  |  | 
View / Search for Courses |  |  |  |  | 
Bidding Cart (add / delete / check out) |  |  |  |  | 
Drop a Bid |  |  |  |  | 
View Student Enrolled Course / Drop a section |  |  |  |  | 
View Bidding Result |  |  |  |  | 
Bootstrap (unzip, validation, insert, error log) |  |  |  |  | 
Start / End Round (Clearing round) |  |  |  |  | 
Student Timetable |  |  |  |  | 
JSON |  |  |  |  | 

## Slide 7: Critical Path

## Slide 8: Critical Path – Iteration 1 ( Week 5)
Requirements
Schedule Planning (1 day)
PM Schedule and PP Planning (1 day)
Identify Manhours needed for each function (1 day)
Design
Design Use Case Diagram (1 day)
Design Logical Diagram (1 day)
Develop Class Diagram (2 days)
Develop Sequence Diagram (2 days)
Start of Iteration
End of Iteration

## Slide 9: Critical Path – Iteration 2 (Week 6)
Design
Design the DB (1 day)
Coding
Login/Logout (1 day)
View All Courses (1 day)
Testing and debugging
View / Search Courses (1 day)
Login / Logout (1 day)
Integration
Integrate Login and View / Search Courses (1 day)
Review SD for Login and View/Search Courses(1 day)
Search Courses (1 day)
Start of Iteration
End of Iteration

## Slide 10: Critical Path – Iteration 3 (Week 7 – 8)
Bootstrap (8 days)
Bidding Cart (2 days)
Start/End Round(2 days)
Drop a section / View Enrolled Courses (2 days)
View Bidding Result (2 days)
Coding
Testing and debugging
Bootstrap (3 days)
Bidding Cart (1 day)
Start/End Round (1 day)
Drop a Section / View Enrolled Courses (1 day)
View Bidding Result (1 day)
Start of Iteration

## Slide 11: Critical Path – Iteration 3 (Week 7 – 8)
Deployment
Integration
Integrate Bootstrap and other functions (1 day)
Deploy onto AWS with current functions (1 day)
Testing and Debugging of errors found during deployment (1 day)
Design
Review SD for current Functions (1 day)
End of Iteration
Iteration continues

## Slide 12
Develop JSON web services
(3 days)
Coding
Develop Student Timetable Function (3 days)
Prepare for Application Demo (3 days)
Testing and debugging
JSON Web Services (1 day)
Critical Path- Iteration 4 (Week 9 – 10)
Integration
Integrate all functionalities (2 days)
Deployment on AWS (1 day)
Deployment
Testing and Debugging after deployment
(2 days)
Student Timetable (1 day)
Requirements
Start of Iteration
End of Iteration

## Slide 13
Design
Review SD for UAT
(1 day)
Coding
Buffer coding period (5 days)
Requirements
Prepare for Supervisor Meeting 2 (1 day)
All functionalities (2 days)
Critical Path- Iteration 5 (Week 11 – 12)
Final deployment AWS for UAT (1 day)
Deployment
Deployment on AWS after testing (1 day)
Testing and Debugging after deployment (2 days)
UAT
(1 day)
Testing and debugging
Start
of
Iteration
End
of Iteration

## Slide 14
Design
Update diagrams
(1 day)
Prepare and rehearse for Final Presentation (1 day)
Requirements
Final Presentation (1 day)
Testing and debugging
Testing and debugging after UAT (2 days)
Critical Path- Iteration 6
(Week 13 - 14)
Create Java docs
(1 day)
Coding
Final deployment on AWS (1 day)
Deployment
Start
of Iteration
End
of Iteration
Final Testing and debugging on AWS (1 day)

## Slide 15: metrics

## Slide 16: Task Metric
Chart: TM Metric Score
| 1 | 2 | 3 | 4 | 5 | 6
Iteration | 1 | 1
Iteration | Total Task | Task Completed | Task Carry Forward
1 | 15 | 15 | 0
2 | 21 | 21 | 0
3 | 75 | 9 | -

## Slide 17: Bug Metric
Chart: Bug Metric Score
| 1 | 2 | 3 | 4 | 5 | 6
Iteration | 0 | 16 | 7

## Slide 18: Mitigation Plan
Iteration | Task | Problem | Mitigation Plan
2 | Login/Logout & Search | Bug Metric > 10 | To schedule more time for debugging and testing for subsequent iterations

## Slide 19: Roles & Responsibilities
Iteration | Week | PM | Pair Programmers 1 |  | Pair Programmers 2 |  | Milestone
1 | 5 | Wilson | NA | NA | NA | NA | -
2 | 6 |  | Ming Kwang | Eugene | Yew Kit | Cristabel | Supervisor Meeting
3 | 7 | Ming Kwang | Wilson | Cristabel | Eugene | Yew Kit | PM Review
 | 8 |  |  |  |  |  | 
4 | 9 | Eugene | Ming Kwang | Cristabel | Wilson | Yew Kit | Application Demo
 | 10 |  |  |  |  |  | 
5 | 11 | Yew Kit | Eugene | Cristabel | Wilson | Ming Kwang | Supervisor Meeting UAT
 | 12 |  |  |  |  |  | 
6 | 13 | Cristabel | Eugene | Wilson | Yew Kit | Ming Kwang | Final Presentation

## Slide 20: Rotation Schedule - PM
Iterations 1 to 2 (Week 5 & 6)
  Each iteration last 1 week
  1 PM throughout both iteration
  PM: Wilson He
Iterations 3 to 6 (Week 7 to 13)
  Each iteration last 2 weeks
  1 PM each iteration
  PM: Ming Kwang, Eugene, Yew Kit, Cristabel

## Slide 21: Rotation Schedule - PP
Each PP is unique to each iteration
  No duplication of PP throughout all iterations
Each PP will be responsible for
  SD for their function
  Testing and debugging for their function

## Slide 22: Thank You!